## CI CD Project 2 Plan
Week | <component> | Difficulty
2020-10-01 | create trello, spread sheet | Easy
2020-10-08 | create github repo, architecture | Easy
2020-10-15 | azure cloud sheel, git hub setup | Easy
2020-10-22 | create makefile, requirement and .yaml file | Easy
2020-10-29 | setup github action and test CI | Easy
2020-11-05 | Setup Flask started code, udacity project2 | Easy
2020-11-12 | setup service connections and make public access available | Easy
2020-11-19 | test make_prediction and make_predict_azure_app | Easy
2020-11-26 | setup web app connection | Easy
2020-12-03 | create self hosted agent | Medium
2020-12-10 | create azure pipeline | Easy
2020-12-17 | deploy the project and test | Easy
| Goals | Goals
Submit Project
Quarterly Plan (Q4) | Submit the project
yearly Plan | Review the code and confirm that it works