## CI CD Project 2 Plan
Week | <component>
2020-10-01 | create trello, spread sheet | done
2020-10-08 | create github repo, architecture | done
2020-10-15 | azure cloud sheel, git hub setup | done
2020-10-22 | create makefile, requirement and .yaml file | done
2020-10-29 | setup github action and test CI | done
2020-11-05 | Setup Flask started code, udacity project2 | done
2020-11-12 | setup service connections and make public access available | done
2020-11-19 | test make_prediction and make_predict_azure_app | done
2020-11-26 | setup web app connection | done
2020-12-03 | create self hosted agent | done
2020-12-10 | create azure pipeline | done
2020-12-17 | deploy the project and test | done
| Goals | Goals